## Sheet1
Sr. No | Task | Task Details | Estimated Time(HRS) | Start Date | End Date | Completion Week
1 | Define | Initial Discussion/ Meetings with concerned depatrments . | 16 | 2019-08-04 | 2019-09-04 | 1st Week
2 | Data Collection | From Prism (Automation) | 32 | 2019-10-04 | 15/04/2019 | 2nd Week
From AG (Manual)
3 | Develop | Loading the data | 80 | 16/04/2019 | 29/04/2019 | 4th Week
Preprocessing Data
Analyzing the data seprate (hit/ clear)
Classifying each State-county Data
Repeating the above process for Prism/ AG dataset.
Combining all the calculated ETA for each state-county combination.
4 | Aplication Integration/ Communication | Communicating through Flask | 32 | 30/04/2019 | 2019-03-05 | 5th Week
5 | Deploy | Deployment to UAT server. | 16 | 2019-06-05 | 2019-09-05 | 5th Week
Deployment to Live server.
6 | Testing | UAT testing | 16 | 2019-10-05 | 2019-12-05 | 6th Week
Live Testing
7 | Evaluate | Validating Predicted ETA with latest request TAT. | 16 | 15/05/2019 | 16/05/2019 | 7th Week
| Buffer Hours |  | 20 |  |  | 8th Week
| Total Hrs |  | 228